## BUG REPORT
Mariners Forex -Bug report
VERSION NO: 1.0, OS: WINDOWS 11, Chrome Version 124.0.6367.119 (Official Build) (64-bit) |  |  |  |  | TESTED BY: Dyuthisree JS
VERIFIED BY: Rakhi |  |  |  |  | DATE: 3 June 2024
BUG ID | EXPECTED RESULT | BUG DESCRIPTION | STEPS TO REPRODUCE | SCREENSHOT | SEVERITY | PRIORITY | STATUS
FLIGHT BOOKING
DEF_MFW_01 | Two separate urls entails different webpage result | homepage and flight booking page is displays the same webpage | 1. https://www.marinersforex.com 2. Click the flights booking Hyperlink i.e. https://www.marinersforex.com/Flights-Booking |  | Major | P2 | New
DEF_MFW_02 | Forex services required as per SRS Document | No forex services listed in the website products | 1. https://www.marinersforex.com 2. Check the home page |  | Critical | P1 | New
DEF_MFW_03 | The phone number displayed should be a clickable link redirecting to a dialer. The arrow must change to hand symbol on mouse hover | 1. The phonenumber does not redirect to a dialer 2. Arrow donot change to hand symbol on mouse hover | 1. https://www.marinersforex.com 2. Check the home page |  | Minor | P3 | New
DEF_MFW_04 | The email id displayed should be a clickable link redirecting to send email. The arrow must change to hand symbol on mouse hover | 1. Doesnot successfully redirect and it is not a clickable link 2. Arrow donot change to hand symbol on mouse hover | 1. https://www.marinersforex.com 2. Check the home page |  | Minor | P4 | New
DEF_MFW_05 | The scrolling text in hot deals must be clickable and must stop on mouse hovering | The scrolling text keeps on moving even after clicking the fight booking ,hotel,bus Hyperlinks | 1. https://www.marinersforex.com 2. Click the Flight booking Hyperlink and check 3. Click the Hotel booking Hyperlink and check 4. Click the Busses in booking Hyperlink and check |  | Minor | P5 | New
DEF_MFW_06 | Scrolling text showing hot deals must characterestics must be as per the SRS document. Hot deals displayed must be customised for each booking | 1. Scrolling text showing hot deals does not completely have the blue background for the whole text . 2. The scrolling hot deals are same for the flight, hotel booking and for busses | 1. https://www.marinersforex.com 2. Click the Flight booking Hyperlink and check 3. Click the Hotel booking Hyperlink and check 4. Click the Busses in booking Hyperlink and check |  | Minor | P6 | New
DEF_MFW_07 | The sliding card displays must be customised for each booking type | 1. The sliding card display is same for flight booking,hotel and bus bookings page. 2. The displays of locations shown are all geneic data and doesnot show customised data | 1. https://www.marinersforex.com 2. Click the Flight booking Hyperlink and check 3. Click the Hotel booking Hyperlink and check 4. Click the Busses in booking Hyperlink and check |  | Major | P2 | New
DEF_MFW_08 | Sliding card display must show hotel or bus or flight details | 1. Card displays properties not hotels or flights or busses | 1. https://www.marinersforex.com 2. Click the Flight booking Hyperlink and check 3. Click the Hotel booking Hyperlink and check 4. Click the Busses in booking Hyperlink and check |  | Minor | P3 | New
DEF_MFW_09 | The travel planning mega menu is displays flight details which must be displayed only in the flight booking Hyperlink | Flight planning mega menu displayed is common in all the Hyperlinks is displayed in all Hyperlinks | 1. https://www.marinersforex.com 2. Click the Flight booking Hyperlink and check 3. Click the Hotel booking Hyperlink and check 4. Click the Busses in booking Hyperlink and check |  | Minor | P3 | New
DEF_MFW_10 | The start your travel planning mega menu must be as per the SRS document | Airport Acronyms may not be very userfriendly . | 1. https://www.marinersforex.com 2.Scroll down to Start your travel planning here menu |  | Enhancment | P4 | New
DEF_MFW_11 | The start your travel planning mega menu must be as per the SRS document | Flight planning mega menu displays only limited selection | 1. https://www.marinersforex.com 2.Check the homepage 3. Scroll down to Start your travel planning here menu and check |  | Minor | P3 | New
DEF_MFW_12 | The start your travel planning mega menu the down arrow button must show various options and must be a clickable hyper link, also during mouse hower the arrow must change to hand symbol | 1. Drop down arrow given is not a clickable hyperlink 2. There is no drop down menu 3. There is no change during mouse hover | 1. https://www.marinersforex.com 2. Check the home page 3. Scroll down to Start your travel planning here menu and check |  | Minor | P3 | New
DEF_MFW_13 | Search and booking of hotels name must be displayed under the hotel booking Hyperlink | Search and book hotels is displayed in the main content for flight booking, and busbooking Hyperlinks | 1. https://www.marinersforex.com 2. Click the Flight booking Hyperlink and check 3. Click the Hotel booking Hyperlink and check 4. Click the Busses in booking Hyperlink and check |  | Minor | P3 | New
DEF_MFW_14 | Chatbot should display options as per the SRS document | Displays Cab,Train,Tour,and others which is extra and not as per the SRS document | 1. https://www.marinersforex.com 2. Click on the round chatbot at the bottom right corner |  | Minor | P3 | New
DEF_MFW_15 | Chatbot should accept real email ids only and reject invalid email ids and display error message | Chatbot accepts invalid domain name for email id and donot display error message, instead went on to the next question | 1. https://www.marinersforex.com 2. Click on the round chatbot at the bottom right corner 3. When asked for name enter:"GYUS" 4. When asked for phone number, Provide phone number as 1234567890 5. On asking to enter the email adress Enter gyus@regiffmail.com |  | Minor | P3 | New
DEF_MFW_16 | Chatbot should display options as per the SRS document | Displays options like Forex,Raja AI chatbot and Remittance which are not available as per the SRS document | 1. https://www.marinersforex.com 2. Click on the round chatbot at the bottom right corner 3. When asked for name enter:"GYUS" 4. When asked for phone number, Provide phone number as 1234567890 5. On asking to enter the email adress Enter gyus@regiffmail.com |  | Major | P2 | New
DEF_MFW_17 | All the details under the flight hyperlink must be as per the SRS document | The drop down does not fully cover all the options till the premium economy | 1. https://www.marinersforex.com 2. Click the Flight booking Hyperlink 3. check the Travellers and classes drop down |  | Trivial | P4 | New
DEF_MFW_18 | There must be option to choose flights for Adult , Children, Senior Citizens, Army Personnel | There is no option to choose flights for Senior Citizens and Army Personnel | 1. https://www.marinersforex.com 2. Click the Flight booking Hyperlink 3. Click on Travellers and classes drop down and check |  | Major | P2 | New
DEF_MFW_19 | All the details should be consistent | The date in the flight booking page when accessed through searching in the flights hyperlink is not same as that when accessed through ''Start your travell planning here" mega menu | 1. https://www.marinersforex.com 2. Click the Flight booking Hyperlink 3. Click on Travellers and classes drop down 4. Select FROM Field as Srinagar and To field as (IXC) Chandigarh 4. Select 1 adult by clicking + symbol 5. Select economy from the toggle button 6. Click search and check the date displayed on flight booking page is todays date 7. Go to home page by clicking the Main Logo 8. Scroll down to the "start your travel planning here" mega menu and under (SXR) srinagar click on chandigarh 9. Check the date on the flight booking page |  | Major | P2 | New
DEF_MFW_20 | The details selected from the Travellers/classes drop down menu should be displayed after clicking the done button | The details selected from the Travellers/classes drop down menu is not displayed after selection from the drop down pane | 1. https://www.marinersforex.com 2. Click the Flight booking Hyperlink 3. check the Travellers and classes drop down 4. In the drop down in the toggle menu select Economy class and Add one Adult for travel 5. Click Search 6. Check the Travellers / Classess field |  | Minor | P3 | New
DEF_MFW_21 | International Holiday destinations to be featured under the International holidays tab | The sliding card display below International holidays features domestic tour packages like GOA and Kerala | 1. https://www.marinersforex.com 2. Scroll down and check the international Holidays |  | Trivial | P4 | New
DEF_MFW_22 | International holiday destinations featuring card slider must be a clickable hyperlink and redirect to the corresponding page | On clicking the international destination card the sliding card resets but is not a clickable hyperlink | 1. https://www.marinersforex.com 2. Scroll down and check the international Holidays card 3. Click on the card |  | Trivial | P4 | New
DEF_MFW_23 | Information displayed int the website should be as per the SRS document | Address mismatch. Should be written as India, Dubai and USA to keep the format right | 1. https://www.marinersforex.com 2. Check the footer |  | Trivial | P4 | New
DEF_MFW_24 | The website charcteristics must match as per the SRS Document | 1. The image is a clickable hyperlink but redirects to https://marinersforex.com/online/Contact-Us 2. The redirected page is not blank only the chatbot is visible | 1. https://www.marinersforex.com 2. Scroll down and checkbelow the sliding card featuring travel blogs to find the image as shown in the screenshot 3. Click on the image |  | Major | P2 | New
DEF_MFW_25 | The sliding cards featured in Travel Blogs must be a clickable link and arrow must change on mouse hover | The sliding card is not a clickable link | 1. https://www.marinersforex.com 2. Scroll down and check the sliding card featuring travel blogs 3. Click on the card |  | Minor | P3 | New
DEF_MFW_26 | All the characteristics of flight booking must be as per the SRS document | The number of the flights displayed donot change according to the result displayed | 1. https://www.marinersforex.com 2. Click the Flight booking Hyperlink 3. Check all the fields have been prefilled with default values 4. Click Search 5. In the Airline toggle menu select Vistara airlines logo and check the number of flights in Paranthesis 6. In the Airline toggle menu select Airindia airlines logo and check the number of flights in Paranthesis 7. In the Airline toggle menu select Spiceject logo and check the number of flights in Paranthesis |  | Major | P2 | New
DEF_MFW_27 | All the characteristics of flight booking must be as per the SRS document | The toggle selector in the Flight booking cannot be selected for more than one options. | 1. https://www.marinersforex.com 2. Click the Flight booking Hyperlink 3. Check all the fields have been prefilled with default values 4. Click Search 5. In the Airline toggle menu select Vistara airlines logo and again select Airindia airlines logo |  | Major | P2 | New
DEF_MFW_28 | All the characteristics of flight booking must be as per the SRS document | On selecting all the options in the stops toggle no result is displayed as 'sorry no flight Found " instead of showing all results . | 1. https://www.marinersforex.com 2. Click the Flight booking Hyperlink 3. Check all the fields have been prefilled with default values 4. Click Search 5. In the Stops toggle menu select Direct and check 6.Then in Stops toggle menu select 1and check the display 7. Then again in the stops toggle menu select 2 or more and check the result |  | Major | P2 | New
DEF_MFW_29 | The displayed results must conform to the selection done by the user | In the toggle select under the outbound flight times select the option Morning (4:00 to 11:00) . It still shows the flights after 11:00 am | 1. https://www.marinersforex.com 2. Click the Flight booking Hyperlink 3. Check all the fields have been prefilled with default values 4. Click Search 5. In the Outbound flight times toggle menu select Morning (4:00 to 11:00) and check the result |  | Major | P2 | New
DEF_MFW_30 |  | In the toggle select under the outbound flight times select the option Evening (16:00 to 21:00) . It shows the flights after 21:00 | 1. https://www.marinersforex.com 2. Click the Flight booking Hyperlink 3. Check all the fields have been prefilled with default values 4. Click Search 5. In the Outbound flight times toggle menu select and deselect the option Evening (16:00 to 21:00) and check the result |  | Major | P2 | New
DEF_MFW_31 | The flight details displayed must be uptodate and updated by the time of checking | In the toggle select under the outbound flight times select the option Night (21:00 to 04:00) . It still shows there are no flights, but when the option is not selected there are flights after 21:00 | 1. https://www.marinersforex.com 2. Click the Flight booking Hyperlink 3. Check all the fields have been prefilled with default values 4. Click Search 5. In the Outbound flight times toggle menu select Night (21:00 to 04:00) and check the result 6. In the Outbound flight times toggle menu deselect Night (21:00 to 04:00) and check the result |  | Major | P2 | New
DEF_MFW_32 | Flight booking should be possible without any falws | Unable to book a flight ticket. An error is displayed "Technical error has been found please contact Supplier or try again" | 1. https://www.marinersforex.com 2. Click the Flight booking Hyperlink 3. Check all the fields have been prefilled with default values 4. Change the date to 27/05/2024 5. Click Search 6. Click Book Now in the first option. 7. In the field "Email id" Enter - bokdwiju@gmail.com 8. Select title field select Mr. 9. In the First name field enter "Gwi Ju" 10. In the LAst NAme Enter "Bok" 11 Click Continue |  | Critical | P1 | New
DEF_MFW_33 | Clear all filter option must be a clickable hyperlink | 1. Clear all filter option is not a clickable hyper link 2. The mouse arrow does not change on mouse hover over the target | 1. https://www.marinersforex.com 2. Click the Flight booking Hyperlink 3. Check all the fields have been prefilled with default values 4. Change the date to 27/05/2024 5. Click Search 6.Mouse hower over the clear all filters option |  | Major | P2 | New
HOTEL BOOKING
DEF_MFW_34 | The selection panes should be in alphabetical order | The list of location of hotels selection pane is not in the alphabetical order | 1. https://www.marinersforex.com 2. Click the Hotel booking Hyperlink and check 3. Click on the field 'Where are you going?' and check |  | Enhancement | P5 | New
DEF_MFW_35 | All Details in website must be present as per the SRS document | The list of locations are incomplete. Locations available in india are those that starts with A only | 1. https://www.marinersforex.com 2. Click the Hotel booking Hyperlink and check 3. Click on the field 'Where are you going?' and check 4. Enter India and check |  | Major | P2 | New
DEF_MFW_36 | The travellers field must display number of travellers and rooms | 1 room is selected by default but number of travellers not displayed The number of adults is 0 by default | 1. https://www.marinersforex.com 2. Click the Hotel booking Hyperlink and check 3. Check the Field Travellers 1 Room |  | Minor | P3 | New
DEF_MFW_37 | The number of adults and childs displayed must be 0 or more. Number of adult must be 1 by default | Even -1 ,-2 are displayed in selection pane for number of adults | 1. https://www.marinersforex.com 2. Click the Hotel booking Hyperlink and check 3. Click the Field Travellers 1 Room 4 Click '-' symbol selecting the number of Adult 5. Check by clicking beyond the value 0 is displayed |  | Major | P2 | New
DEF_MFW_38 | on clicking the minus sign when the selection pane for selecting number of child is 0, the number should not decrease further. The display must not change | On clicking the '-' symbol under child , case when number of child displayed is 0 the page gets redirected to a blank page | 1. https://www.marinersforex.com 2. Click the Hotel booking Hyperlink and check 3. Click the Field Travellers 1 Room 4 Click '-' symbol on selecting the number of Children when the display is 0 |  | Major | P2 | New
DEF_MFW_39 | All fields must be aligned and visually appealing | One addding more than for 4 children the age field spills over the outline of the selection pane | 1. https://www.marinersforex.com 2. Click the Hotel booking Hyperlink and check 3. Click the Field Travellers 1 Room 4 Click '-' symbol on selecting the number of Children when the display is 0 |  | Minor | P3 | New
DEF_MFW_40 | Hotels must be displayed for the correct location for which hotel is searched for | No list of hotels is displayed when hotels is searched. | 1. https://www.marinersforex.com 2. Click the Hotel booking Hyperlink and check 3. Click in the field where are you going 4. Select the first location in the dropdown 5. Click the first date field 6. Select start date by clicking the calender and leaving date by clicking another date 7. Click the Field Travellers 1 Room 8 Click '+' symbol on selecting the number of Adults as 1, Click done 9. Click Search hotel |  | Critical | P1 | New
DEF_MFW_41 | All Details in website must be present as per the SRS document | On entering values in the Hotel Name field the webpage contents zoom in | 1. https://www.marinersforex.com 2. Click the Hotel booking Hyperlink and check 3. Click in the field where are you going 4. Select the first location in the dropdown 5. Click the first date field 6. Select start date by clicking the calender and leaving date by clicking another date 7. Click the Field Travellers 1 Room 8 Click '+' symbol on selecting the number of Adults as 1, Click done 9. Click Search hotel 10. In the filters section Hotel name field enter character " a" |  | Major | P2 | New
DEF_MFW_42 | All Details in website must be present as per the SRS document | On entering values in the Hotel Location field the webpage contents zoom in | 1. https://www.marinersforex.com 2. Click the Hotel booking Hyperlink and check 3. Click in the field where are you going 4. Select the first location in the dropdown 5. Click the first date field 6. Select start date by clicking the calender and leaving date by clicking another date 7. Click the Field Travellers 1 Room 8 Click '+' symbol on selecting the number of Adults as 1, Click done 9. Click Search hotel 10. In the filters section Hotel Location field enter character "a" |  | Major | P2 | New
DEF_MFW_43 | All Details in website must be present as per the SRS document | Clicking on the rating field also zooms the webpage contents | 1. https://www.marinersforex.com 2. Click the Hotel booking Hyperlink and check 3. Click in the field where are you going 4. Select the first location in the dropdown 5. Click the first date field 6. Select start date by clicking the calender and leaving date by clicking another date 7. Click the Field Travellers 1 Room 8 Click '+' symbol on selecting the number of Adults as 1, Click done 9. Click Search hotel 10. Click any rating star |  | Major | P2 | New
BUS BOOKING
DEF_MFW_44 | All Details in website must be present as per the SRS document | The list of location must be displayed in selection pane of the FROM Field - here only delhi is displayed as default -no other options is present | 1. https://www.marinersforex.com 2. Click the Busses booking Hyperlink and check 3. Click on the field 'From' and check |  | Major | P2 | New
DEF_MFW_45 | All Details in website must be present as per the SRS document | The list of location must be displayed in selection pane of the TO field- here there is no default display | 1. https://www.marinersforex.com 2. Click the Busses booking Hyperlink and check 3. Check the field 'To' |  | Major | P2 | New
DEF_MFW_46 | All Details in website must be present as per the SRS document | The list of location must be displayed in selection pane of the TO field- here there is no default display - no other options is present | 1. https://www.marinersforex.com 2. Click the Busses booking Hyperlink and check 3. Click on the field 'To' and check |  | Major | P2 | New
DEF_MFW_47 | All Details in website must be present as per the SRS document | The Search Busses Tab do not work on clicking. It does not redirect | 1. https://www.marinersforex.com 2. Click the Busses booking Hyperlink and check 3. Click on the field 'To' and check 4. Select date 30/5/2024 |  | Critical | P1 | New
DEF_MFW_48 | All Details in website must be present as per the SRS document | Footer is not visible always | 1. https://www.marinersforex.com 2. Check the footer |  | Major | P2 | New
SIGNUP AND LOGIN
DEF_MFW_49 | All Details in website must be present as per the SRS document | IN SIGNUP page for travellers pane agency name field is present | 1. https://www.marinersforex.com 2. Click the Login and sign up button 3. Click travellers hyperlink and click SignUP |  | Minor | P3 | New
DEF_MFW_50 | All Details in website must be present as per the SRS document | IN SIGNUP page for travellers pane the mobile number field up down key is given which is useless in case of mobile numbers | 1. https://www.marinersforex.com 2. Click the Login and sign up button 3. Click travellers hyperlink and click SignUP 4.Check the Mobile number field |  | Major | P2 | New
DEF_MFW_51 | All Details in website must be present as per the SRS document | IN SIGNUP page for travellers pane the mobile number field up only +91 is shown and it cannot be changed. | 1. https://www.marinersforex.com 2. Click the Login and sign up button 3. Click travellers hyperlink and click SignUP 4.Check the Mobile number field |  | Major | P2 | New
DEF_MFW_52 | All Details in website must be present as per the SRS document | In mobile number field negative value can also be inserted | 1. https://www.marinersforex.com 2. Click the Login and sign up button 3. Click travellers hyperlink and click SignUP 4.Check the Mobile number field 5. Click the down button |  | Major | P2 | New
DEF_MFW_53 | The signup functionality must work properly receic\ve inputs and create account | On completing all the fields and clicking the create account an error message shows that Firstname ,Last name ,emailand password fields are empty | 1. https://www.marinersforex.com 2. Click the Login and sign up button 3. Click travellers hyperlink and click SignUP 4. In Firstname field enter"Krishna" 5. In last name field "Gopal" 6.Pannumber field input 123456789632 7.Agency name : tharakans 8.Email id field input "krishna@rediffmail.com" 9.Mobile number field enter 8754212145 10. Password qwe123 11. Confirm passwor enter qwe123 12. ClickCREATE ACCOUNT |  | Critical | P1 | New